TIME LINE FOR SEVEN-WEEK PROGRAM

Month One

Prepare article for newsletter

Month Two

Prepare bulletins

Prepare affirmation cards (single for personal use, or double so one side can be displayed at the church)

Arrange for host homes for study groups

Arrange for facilitators for study groups

Create art for sanctuary (photos, weekly themes, etc.)

Order copies of Gandhi the Man from Nilgiri Press (Tel:  1-800-475-2369)

Month Three

Put out sign-up sheets for Study Groups

Arrange for small group facilitators training

Provide facilitators with facilitator’s guide and 10 copies of each weekly “Study Guide Questions and Notes for Discussion”

Month Four

The program begins

Have copies of past Bulletins and Affirmation cards available

Month Five

The program continues and ends

Thank all volunteers at the end of the program

Optional:  plan a gala banquet or all-church potluck or dessert celebration of the series